## Sheet1
Work Plan: IPF Fellowshop
No. | Activity | March | April | May | June | July | August | September | October | November | December | January | February | March | April
1 | Preparatory Work
1.1 | Informal/formal discussions on proposal with officials/colleagues/experts | bar: March to April
1.2 | Feedback from supervisor/ fellows | bar: May
1.3 | Proposal revised | bar: May
2 | Literature Review
2.1 | Collection and review of secondary literature | bar: April to June
2.2 | Relevant notes | bar: April to June
2.3 | Bibliography | bar: June
2.4 | Table of contents for policy/research paper | bar: June
3 | Primary Data Collection and Analysis
3.1 | Identification of relevant offices and officers | bar: June
3.2 | Establishment of contacts | bar: June to July
3.3 | Collection and review of official documents, archival data etc. | bar: June to July
3.4 | Identification of officers for interviews | bar: June
3.5 | Interviews of officers | bar: July
3.6 | Identification of CSOs/staff for interviews | bar: June
3.7 | Interviews of CSO staff | bar: June to July
3.8 | Identification of legislators for interviews | bar: July
3.9 | Interviews of legislators | bar: August
4 | Reporting
4.1 | Activity report + Research outline | bar: August
4.2 | Interim report | bar: September
5 | Data Collection on Int. Best Practices/ Int. Linkages
5.1 | Identification of institutes/ organizations/ individuals to visit abroad | bar: June to July
5.2 | Visit to India for contacts/data collection | bar: August
5.3 | Visit to UK for contacts/ data collection | bar: October
5.4 | Visit to North/Eastern Europe for contacts/ data collection | bar: October
6 | Preparation of Policy Paper
6.1 | First draft prepared | bar: October to November
6.2 | First draft shared with advisors/ others for feedback | bar: November to December
6.3 | Talks given/ organized to share tentative findings and obtain feedback | bar: December
6.4 | Draft finalized & posted on website | bar: January
6.5 | Lay-out and designing of policy paper | bar: January
6.6 | Policy paper published | bar: February
7 | Research Papers
7.1 | Draft paper | bar: September to January
7.2 | Draft shared with advisors/others foe feedback | bar: January to February
7.3 | Draft finalized | bar: February to March
7.4 | Finalized paper submitted | bar: March
8 | Dissemination of findings/ policy paper
8.1 | Launch of policy paper | bar: March
8.2 | Talks at other forums | bar: January to March
8.3 | Dissemination through post etc. | bar: March
9 | Final Report
9.1 | Activity report and final research paper | bar: March
10 | Training III | bar: April