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	Activities


	Period

	· IPF workshop 

· Meetings with mentors: discussing the topic of the research. 

· Justifying approaches and methodology. 


	04.03.03 – 12.03.03

	· Meeting with the local mentor. 

· Traveling to Astana to held Meetings at the Parliament, and Presidential Administration for testing the relevance of the research topic and research questions.  


	24 –25.03.03

	· Reading, justifying the research design.

· Communication with the mentors via e-mail, phone.

· Traveling to Astana.  Meeting with the local mentor. Meeting in the Ministry of Finance to discuss the relevance of reconsidered focus of the research.

· Reconsideration of the focus of the research and cases of the study.


	April – May 2003

	· IPF workshop 

· Meetings with mentors, reporting, discussing the progress of the research.


	02.06.03 – 12.03.03 

	· Reading, development of the instruments of the research, the interim Research Paper development. 

· Communications with the mentors via e-mail and phone.


	12.06.03 – 30.08.03

	· Interviews with government officials and experts

· Conduction of survey of population regarding their awareness on fully funded pension system 

· Writing the Paper


	01.09.03 – 20.01.04

	· Sending the draft to the mentors (local and international)


	20.01.04 

	· Establishing of the Kazakhstani Association of Pension Funds Contributors. This association was established as an outcome of the research project. Its mission is to represent the voice of contributors as actors of the policy process around the issues of pension reform.


	January of 2004

	· Receiving comments from the mentors (local and international)


	10.03.04

	· Making adjustments to the research paper 

· Conduction of expert poll and the second survey of population on the perception and failures/success of FF pension system

· Preparation to the Round table Social Aspects of the Development of FF Pension System in Kazakhstan 


	February – March 2004

	· Participation in the final workshop in Budapest 


	24-28.03.04

	· Conduction of the Round table Social Aspects of the Development of FF Pension System in Kazakhstan

The Round table was organized by the Association. It gathered top-managers of pension funds, representatives of government agencies (Agency on regulation of Financial Market and Financial Institutions, Ministry of Finance, Ministry of Economy and Budget Planning, State Center of Pension Payments), experts (World Bank, Pragma Corporation (USAID)), parliament members, trade unions, political parties and media.

The event had a wide coverage in the national and local media. The report about the Round table was shown at 4 national and 3 local TV stations. Also there were articles in national and local newspapers (copies are enclosed).


	06.04.04

	· Writing the Policy Paper 

· Communicating with the local and group mentors


	April 2004

	· Submission of the final activity report to IPF


	April, 25 2004


