Eastern Europe Economic Transition Policy Revisited: The Neoschumpeterian model

Dr. Ivan Tchalakov – 2003 IPF Research proposal

#### PROJECT TIMETABLE

| Period of time | Activity |
| --- | --- |
| March 15 - April 30, 2003 (One months research stay at IFF/IFZ-Graz, Austria) | Clarifying methodology - Bibliographical search on sectorсal economic analysis and policy initiatives in Central and Eastern Europe; Collecting macroeconomic statistical dada for the sectors of information technologies, pharmaceutical and food industries; Building database of relevant firms |
| May 1 - June 30, 2003 (Two- three weeks research stay at CPS, Budapest) | Clarifying methodology - Consultations with relevant staff from CEU-CPS & Soros foundations networks. Secondary analysis of the relevant economic and sociological research on SME in Bulgaria; Selection of the firms to be studied (from the sectors of information technologies, pharmaceutical and food industries) |
| July 1- 30, 2003 | Consultations with experts in each of the three sectors; Design of the interview; Test interviews with firms' managers |
| August 20 - October 20,2003 | Interviews with firms' managers and economic policy makers; Preliminary treatment of the collected quantitative and qualitative data. Building firms' database. |
| October 21 - December 20, 2003 (Two- three weeks research stay at CPS, Budapest) | Data analysis and preliminary report. Elaboration of Dissemination and Policy actions plan. |
| January 1 - March 15, 2004 | Final report with project results. Dissemination: Publishing booklet with provisional title "Sectorial Economic Policy and Economic Growth". Publishing of series of smaller papers on the sectors' successful stories. Panel discussion with representatives of branch associations in studied industries and government/local government officials. Presentation of project results at relevant forums of CEU-CPS and Soros foundations network. |

back to home